## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Your Name | 2026-01-10 | Login button does not respond when clicked on Chrome browser. Expected: User should be logged in and redirected to dashboard. Actual: Button appears unresponsive, no action occurs. | Sprint 1 | YUVARAJ | Functional | Fixed onclick event handler - removed conflicting Cloudflare script tag from HTML | 2026-01-11 | Closed | Retested on Chrome and Firefox - working fine
2 | Your Name | 2026-01-15 | Popular products section shows error 'No popular_products in response'. Expected: Display 6 popular products with images. Actual: API returns 'popular_items' but frontend expects 'popular_products'. | Sprint 2 | YUVARAJ | Functional | Updated API endpoint in app.py to return 'popular_products' instead of 'popular_items' | 2026-01-15 | Closed | JSON key mismatch resolved
3 | Your Name | 2026-01-18 | Product images not displaying on product cards. Expected: Each product card should show a 400x300 image. Actual: Images show broken placeholder. | Sprint 2 | YUVARAJ | UI | Added image_url field to all API responses using Picsum Photos service | 2026-01-18 | Closed | Images now load correctly with lazy loading
4 | Your Name | 2026-01-22 | Recommendations API returns JSON error 'Unexpected token -Infinity'. Expected: Valid JSON with predicted scores. Actual: NMF model returns -Infinity for already-rated items. | Sprint 3 | YUVARAJ | Functional | Added filter to remove -Infinity scores before JSON serialization in get_user_recommendations() | 2026-01-23 | Closed | All scores now properly formatted
5 | Your Name | 2026-01-25 | Database shows 'no such table: users' error on first run. Expected: Database tables created automatically. Actual: Tables not initialized. | Sprint 3 | YUVARAJ | Data | Created init_db.py script and updated app.py to auto-initialize tables on startup | 2026-01-25 | Closed | Added to deployment documentation
6 | Your Name | 2026-01-28 | New user registration fails with 'username already exists'. Expected: New users can register with unique usernames. Actual: Demo users created in-memory causing conflicts. | Sprint 3 | YUVARAJ | Functional | Migrated from in-memory storage to SQLite database with proper user management | 2026-01-29 | Closed | 10 demo users pre-created in database
7 | Your Name | 2026-02-02 | User-item matrix shows index out of bounds error. Expected: Matrix user_id maps to database user. Actual: Database user_id used directly without mapping. | Sprint 4 | YUVARAJ | Functional | Added matrix_user_id field to users table to map database IDs to matrix rows | 2026-02-02 | Closed | Demo users now map to matrix rows 0-9
8 | Your Name | 2026-02-05 | API URL must be manually configured for deployment. Expected: Auto-detect API URL. Actual: Users must update URL manually in HTML. | Sprint 5 | YUVARAJ | Performance | Implemented auto-detection function that tests multiple URLs with 3s timeout | 2026-02-06 | Closed | Works on localhost and deployed environments
9 | Your Name | 2026-02-06 | Product card layout breaks on mobile devices below 375px width. Expected: Responsive grid layout. Actual: Images overflow container. | Sprint 5 | YUVARAJ | UI | Updated CSS media queries and changed grid-template-columns for small screens | 2026-02-07 | Open | Waiting for mobile device testing
10 | Your Name | 2026-02-07 | Session expires immediately after login on some browsers. Expected: Session lasts 7 days. Actual: Token not properly stored in localStorage. | Sprint 5 | YUVARAJ | Functional | Fixed token storage and retrieval logic in login() function | 2026-02-08 | Closed | Tested on Chrome | Firefox | Safari
11 | Your Name | 2026-02-08 | Similar products feature returns empty array for some items. Expected: 5 similar products based on NMF factors. Actual: Index out of bounds when item_id >= matrix columns. | Sprint 5 | YUVARAJ | Functional | Added boundary check in get_similar_items() before accessing item_factors | 2026-02-08 | Closed | Now returns appropriate fallback
12 | Your Name | 2026-02-09 | File upload for model files (.pkl, .npz) fails on Railway deployment. Expected: Model files loaded on startup. Actual: Files not found in deployment. | Sprint 5 | YUVARAJ | Compatibility | Added model files to .gitignore exceptions and verified Railway build includes them | 2026-02-09 | Open | Testing on staging environment

## Sheet2
Logical
User Interface
Maintainability
Standards
Others